## Gantt
Lofthus frukt og saft |  |  | Dates | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15
|  |  | Weeks | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11
|  |  | Days | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Thursday | Wednesday | Thursday | Friday | Saturday | Sunday
|  | Service |  | i | i | i | i | i |  |  | a
|  | Designing | [8 empty] | i | i | i | i | i
(s) | Indicates Initial timeframe | Building | [15 empty] | i | i | i | i | i |  |  | I | I | I | I | I |  |  | i | i | i | i | i |  |  | a
(a) | Indicates Additional timeframe | Back-End | [36 empty] | i | i | i | i | i |  |  | i | i | i | i | i
|  | Publishing/Finalizing | [50 empty] | i | i | i | i | i |  |  | i | i | i | i | i |  |  | i | i | i | i | i |  |  | i | i | i | i | i
Task | Name, Head of dep | Department(s)
Service
Find Host | Anette Stustad | Manager, Front End |  | s | s | a | [74 empty] | 3
Search For Domain | Ine Jakobsen | Back End |  |  | s | s | a | [73 empty] | 3
Register Domain | Ine Jakobsen | Back End |  |  |  | s | s | s |  |  | a | [69 empty] | 4
Designing
Get relevant images for page | Øyvind Dahl | Photographer, Front End | [8 empty] | s | a | [68 empty] | 2
Copyright page content | Kent Samuelsen | Copywriter, Front End | [9 empty] | s | s | a | [66 empty] | 3
Design Icons | Johan Forsebakk | Front End | [8 empty] | s | s | s | s | a | [65 empty] | 5
Design Default Template | Kent Samuelsen | Copywriter, Front End | [8 empty] | s | s | a | [67 empty] | 3
Choose Fonts | Kent Samuelsen | Copywriter, Front End | [10 empty] | s | s | a | [65 empty] | 3
Meeting with Customer | Anette Stustad | Manager, Front End | [15 empty] | s | [62 empty] | 1
Create VCS | Ine Jakobsen | Back End | [16 empty] | s | s | a | [59 empty] | 3
Compose design | Anette Stustad | Manager, Front End | [16 empty] | s | s | a
Compose XD Mockup | Anette Stustad | Manager, Front End | [17 empty] | s | s | a
Building
Build Standard HTML | Johan Forsebakk | Front End | [22 empty] | s | s | a | [53 empty] | 3
Build Standard CSS | Johan Forsebakk | Front End | [23 empty] | s | s | a | [52 empty] | 3
Build Standard JS | Kent Samuelsen | Copywriter, Front End | [24 empty] | s | s | a | [51 empty] | 3
Build Home page | Anette Stustad | Manager, Front End | [29 empty] | s | s | a | [46 empty] | 3
Build About page | Anette Stustad | Manager, Front End | [30 empty] | s | s | a | [45 empty] | 3
Build Contact page | Øyvind Dahl | Photographer, Front End | [29 empty] | s | s | a | [46 empty] | 3
Build Product Page | Øyvind Dahl | Photographer, Front End | [30 empty] | s | s | a | [45 empty] | 3
Build Order Page | Øyvind Dahl | Photographer, Front End | [31 empty] | s | s | a | [44 empty] | 3
Build Account Creation Page | Øyvind Dahl | Photographer, Front End | [32 empty] | s | s |  |  | a | [41 empty] | 3
Add content to pages | Johan Forsebakk | Front End | [32 empty] | s | s |  |  | a | [41 empty] | 3
Finalize content | Anette Stustad | Manager, Front End | [33 empty] | s |  |  | a | [41 empty] | 2
Back-End
Create Founder Acc. | Ine Jakobsen | Back End | [36 empty] | s | a |  |  | a | [37 empty] | 3
Create Worker Acc. | Ine Jakobsen | Back End | [36 empty] | s | a |  |  | a | [37 empty] | 3
Create Consumer Acc. system | Ine Jakobsen | Back End | [37 empty] | s | s | a | a | [37 empty] | 4
Test Order page | Kent Samuelsen | Copywriter, Front End | [43 empty] | s | s |  | a | a | [30 empty] | 4
Test Account Creation page | Kent Samuelsen | Copywriter, Front End | [44 empty] | s | s | a | a | [30 empty] | 4
Final Touches
Meeting to discuss result | Anette Stustad | Manager, Front End | [50 empty] | s | [27 empty] | 1
Discuss meeting with crew | All | All | [51 empty] | s
Apply possible fixes/Adjustments | All | All | [52 empty] | a | a | a
Publishing
Publish to Host | Ine Jakobsen | Back End | [57 empty] | s | s | a | [18 empty] | 3
Open up to official publish | Anette Stustad | Manager, Front End | [58 empty] | s | s | a | [17 empty] | 3
Announce Website | Anette Stustad | Manager, Front End | [59 empty] | s | s | s | [16 empty] | 3
90
| Manpower each week | Total |  | 1 | 2 | 2 | 1 | 1 |  |  | 3 | 3 | 3 | 2 | 0 |  |  | 1 | 2 | 3 | 1 | 0 |  |  | 1 | 2 | 2 | 1 | 0 |  |  | 2 | 4 | 3 | 3 | 3 |  |  | 2 | 1 | 1 | 0 | 0 |  |  | 1 | 2 | 1 | 0 | 0 |  |  | 1 | 1 | 0 | 0 | 0 |  |  | 1 | 2 | 2 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 63

## Network diagram
|  | Concepting |  |  | Designing / Assets |  | Building |  |  | Final preparations |  | Backend | Testing | Publishing
FE Devs 3 | [7 empty] | Build HTML | Build CSS | Add content | Finalize content | Create users | Order Page | Publish to host | Open up to official release | Announce Website
FE Manager 1 (Part of FE) |  |  |  |  | Design and prot webpage | Commune with client, finalize concept | Create VCS | Build website | Build JS |  |  |  | Account creation
Register domain
Client already has Logo and brand strategy |  |  | Search for domain |  |  |  |  | Build Home page |  |  |  | Founder / Admin
|  | Find suitable host for Website |  |  | Design icons |  |  | Build About page |  |  |  | Workers
Names | Special |  |  |  | Design default template |  |  | Build Contact page |  |  |  | Consumers
Anette Stustad | Manager, Front End |  |  |  | Choose fonts |  |  | Build Product page |  |  | Get copyright
Johan Forsebakk | Front End |  |  |  | Get images |  |  | Build Order Page |  |  | Final meeting
Ine Jakobsen | Back End | [6 empty] | Account creation page
Kent Samuelsen | Copywriter, Front End
Øyvind Dahl | Photographer, Front End